## Sheet1
TASK TRACKER
DETECTOR |  |  | ROVER |  |  | NETWORK & INTERFACE
TASK | STATE | REMARK | TASK | STATE | REMARK | TASK | STATE | REMARK
Flash OS | COMPLETE | Use Raspbian Lite in future | Get components |  | Which FC – probably a matek board? | Backend communication framework between hub + units | IN PROGRESS | See readme for explanation of function/directories
Connect & test servos | COMPLETE |  | Flash ardurover |  |  | Frontend – detector unit (rover or static) control interface as webpage |  | webpage with camera views, data/telemetry info from each unit (ie grid ref), some control buttons and warning messages
Install OpenCV and aircrack-ng | IN PROGRESS – INSTALL ON NEW PI | at least 2 means of detection. Find out a way to get data direct from aircrack not string console output | Assemble RC components and connect together |  | Wire & solder basic RC components | Telegram bot | IN PROGRESS | So far the central bot (running on the hub server) seems to work well
Servo control code | IN PROGRESS | Basic servo move commands from hub to unit now work | Test basic remote control of components |  | Go for a test drive! | Set up VPN server |  | All units will connect to this server/”hub” allowing users to control and observe
Test GPS interrupt signal from SDR | IN PROGRESS | Successful transmit. Need test GPS defeat – GPS @ 1.575GHz | Test power pi from 5V pin on FC |  | Make sure to test SDR function | Test issue commands to unit from dislocated network
Test basic SDR operation from pi | COMPLETE | See if SDR can be operated from a pi | Test commands from pi > FC |  | Programmatic control & remote user command
SDR control code |  | Allow for programmatic & dynamic control of RF emission (python subprocess?) | Telemetry over 4G |  | Ardupilot telemetry over 4G
Autorotation |  | Code to pan&scan camera servo | Receive & follow commands over network
Basic image recognition |  | Use pre-existing model as test
Camera-object tracking |  | Servo/camera to track detected object
Acquire drone image dataset |  | Can take many pictures of parrot anafi as test
Train model on dataset
Image recognition test
4G USB setup |  | Install SIM card & PiVPN
4G Data transmission |  | Data & image feed to be visible to users at network hub
Remote user control | IN PROGRESS | Receive & follow commands from network hub
Design servo mount and pi/camera case |  | Current idea: servo in mount below with splayed floorstands; pi, SDR, cam etc in case on top |  |  |  | CREATE MASTER SD CARD |  | Once all necessary software installed and code written, create a master SD card to copy future ones from (create custom OS image maybe?)
Print
Assemble
Full test as assembled