## Sheet1
TASK TRACKER
DETECTOR |  |  | ROVER |  |  | NETWORK & INTERFACE
TASK | STATE | REMARK | TASK | STATE | REMARK | TASK | STATE | REMARK
Flash OS | COMPLETE | Use Raspbian Lite in future | Get components | COMPLETE | Which FC – probably a matek board? | Backend communication framework between hub + units | IN PROGRESS | See readme for explanation of function/directories
Connect & test servos | COMPLETE |  | Flash ardurover | IN PROGRESS | Current board still has INAV | Frontend – detector unit (rover or static) control interface as webpage | IN PROGRESS | webpage with camera views, data/telemetry info from each unit (ie grid ref), some control buttons and warning messages
Install OpenCV and aircrack-ng | COMPLETE | at least 2 means of detection. Find out a way to get data direct from aircrack not string console output | Assemble RC components and connect together | IN PROGRESS | Using PQ-2 | Telegram bot | IN PROGRESS | So far the central bot (running on the hub server) seems to work well
Servo control code | IN PROGRESS | Basic servo move commands from hub to unit now work | Test basic remote control of components |  | Time to fly! | Set up VPN server | COMPLETE | All units will connect to this server/”hub” allowing users to control and observe
Test GPS interrupt signal from SDR | IN PROGRESS | Successful transmit. Need test GPS defeat – GPS @ 1.575GHz | Test power pi from 5V pin on FC |  | Make sure to test SDR function. Can also use 18650 in battery shield | Test issue commands to unit from dislocated network | IN PROGRESS | Don’t remember exactly what I meant but all commands from bot/hub transmit and etc fine
Test basic SDR operation from pi | COMPLETE | See if SDR can be operated from a pi | Test commands from pi > FC | IN PROGRESS | Programmatic control & remote user command
SDR control code |  | Allow for programmatic & dynamic control of RF emission (python subprocess?) | Telemetry over 4G |  | Ardupilot telemetry over 4G
Autorotation |  | Code to pan&scan camera servo | Receive & follow commands over network | IN PROGRESS | Sim testing working well
Basic image recognition |  | Use pre-existing model as test
Camera-object tracking |  | Servo/camera to track detected object
Acquire drone image dataset |  | Can take many pictures of parrot anafi as test
Create & train model on dataset
Image recognition test
4G USB setup | COMPLETE | Wireguard over 4G seems to work
4G Data transmission | IN PROGRESS | Works, just want to be sure of it (ie vid stream and files do send)
Remote user control | COMPLETE | Receive & follow commands from network hub
Design servo mount and pi/camera case |  | Current idea: servo in mount below with splayed floorstands; pi, SDR, cam etc in case on top |  |  |  | CREATE MASTER SD CARD | IN PROGRESS | OS image has been created but need to do final one on raspian-lite when ready
Print
Assemble
Full test as assembled