## Sheet1
TASK TRACKER
DETECTOR |  |  | ROVER |  |  | NETWORK & INTERFACE
TASK | STATE | REMARK | TASK | STATE | REMARK | TASK | STATE | REMARK
Flash OS | COMPLETE | Use Raspbian Lite in future | Get components | COMPLETE | Which FC – probably a matek board? | Backend communication framework between hub + units | COMPLETE | See readme for explanation of function/directories
Connect & test servos | COMPLETE |  | ardupilot | IN PROGRESS | Current board still has INAV | Frontend – detector unit (rover or static) control interface as webpage | IN PROGRESS | webpage with camera views, data/telemetry info from each unit (ie grid ref), some control buttons and warning messages
Install OpenCV and aircrack-ng | COMPLETE |  | Assemble RC components and connect together | COMPLETE | Using PQ-2 model (once built) | Telegram bot | IN PROGRESS | Configure keyboard properly
Servo control code | IN PROGRESS | Basic servo move commands from hub to unit now work | Test basic remote control of components |  | Time to fly! | Set up VPN server | COMPLETE | All units will connect to this server/”hub” allowing users to control and observe
Test GPS interrupt signal from SDR | IN PROGRESS | Successful transmit. Need test GPS defeat – GPS @ 1.575GHz | Test power pi from 5V pin on FC |  | Perhaps better to use 18650 with shield? Compare FC pin with this | Test issue commands to unit from dislocated network | COMPLETE | Don’t remember exactly what I meant but all commands from bot/hub transmit and etc fine
Test basic SDR operation from pi | COMPLETE | See if SDR can be operated from a pi | Test commands from pi > FC | IN PROGRESS | Programmatic control & remote user command
SDR control code |  | Allow for programmatic & dynamic control of RF emission (use subprocess or library?) | Telemetry over 4G | IN PROGRESS | Seems to work fine over VPN
Autorotation |  | Code to pan&scan camera servo | Receive & follow commands over network | IN PROGRESS | Sim testing working well
Basic image recognition | COMPLETE | Use pre-existing model as test
Camera-object tracking |  | Servo/camera to track detected object
Acquire drone image dataset | COMPLETE | Plenty of images downloaded by auto downloader script
Create & train model on dataset
Image recognition test
4G USB setup | COMPLETE | Wireguard over 4G seems to work
4G Data transmission | IN PROGRESS | Works, just want to be sure of it (ie vid stream and files do send)
Remote user control | COMPLETE | Receive & follow commands from network hub
Design servo mount and pi/camera case | IN PROGRESS | Have designed a payload container for testing for now, later need to design with servo mounts & rotating camera |  |  |  | CREATE MASTER SD CARD | IN PROGRESS | Need to add wireguard to latest OS image
Print | IN PROGRESS | Printing provisional/testing Rpi payload container
Assemble
Full test as assembled